## Sheet1
#NAME? | TESTCASE | STATUS | UAT FEEDBACK | AXXIS BA COMMENTS
Policy issueance | Policy - Quote Approval - Underwriter to Review & Approve Quote (Maker - checker) | Not run | Authority matrix, not implemented | Responded on email - Response No. 5 - On approval matrix
| Policy -Quote checks- Quotes should have an expiration period - Verify handling of expired quotations | Pending Demo |  | Work in progress - Axxis
| Policy -Quote checks- Expired quotes should not be retrievable - Verify system behavior for expired quotations : | Pending Demo |  | Work in progress - Axxis
| Policy issuance - System should allow authorized approvals - Verify back-office approval workflows for policy issuance ¦ Steps: | Not run | Maker checker - approval matrix needs to be implemented | Responded on email - Response No. 5 - On approval matrix
| Policy issuance - Quick Quote Validations - Ensure all mandatory fields are validated, IPRS | Fail | able to create a client at quick quote without all valiadations as required in the Contact Module | Work in progress - Axxis
| Policy issuance - Business Rule - Validate all approvals as per EGIK Proposed approval matrix for policy issuance | Cautioned | Matrix not yet uploaded | Responded on email - Response No. 5 - On approval matrix
Policy Renewal | Policy Renewal - Verify that the system identifies policies due for renewal | Pending Demo | this was not demonstrated | Demo donoe today - 22/05/2025
| Renewal - First Renewal Notice (90 Days Before Renewal Date) -Verify system sends renewal notice 90 days before renewal date. | Pending Demo | this was not demonstrated | Demo donoe today - 22/05/2025
| Renewal - Second Renewal Notice (30 Days Before Renewal Date) -Verify system sends renewal notice 30 days before renewal date. | Pending Demo | this was not demonstrated | Demo donoe today - 22/05/2025
| Renewal - Final Renewal Notice (7 Days Before Renewal Date) - Verify system sends final renewal notice 7 days before renewal date. | Pending Demo | this was not demonstrated | Demo donoe today - 22/05/2025
| Renewal - Tax Calculation and Posting - Ensure system calculates and posts applicable taxes. | Not run | Pending Demo | Finance Demo - Ogoing (Brian to conclude)
| Policy issuance - System should process cancellations and issue refunds per policy - Verify cancellation and refund policy execution ¦ Steps: | Fail | not able to refund to the customer, (Unable to cancel renewed policy) | Responded on email - Response No. 2
Policy cancellation | Policy Cancellation - System should allow cancellation if no arrears exist - Verify that a policy can be successfully canceled | Cautioned | unable to cancel a policy where credit endorsement has been done | Responded on email - Response No. 3
Endosement | Endosement- System should generate an endorsement schedule and send via email. - Verify Endorsement Schedule Generation and Email Dispatch | Pass | description not being picked/auto generated | Pass - OK
| Endosement- Endorsement request should become inactive after 14 days if payment is not made. - Verify Inactivity Rule for Unpaid Endorsements | Fail | NO Demo has been done | Pending business decision and feedback
| Policy issuance - Business Rule - Validate all approvals as per EGIK Proposed approval matrix for all endorsements | Cautioned | not mapped | Responded on email - Response No. 5 - On approval matrix
Claims | Claim Processing Business Rules Validation - System should allow reserve revisions up or down, and closed claims should have zero reserves. - Verify that reserve amounts can be revised throughout the claim process. | Cautioned | claim is only closing for declined claims and not closed claims | Responded on email - Response No. 6
| Claim Processing Business Rules Validation - Claim number should be the primary reference for claim posting, reserving, and payment processing. - Verify that the claim number is used as the main reference for claim processing. | Cautioned | the BRD was very clear on this requirement
| Policy issuance - Business Rule - Validate all approvals as per EGIK Proposed approval matrix for all claims | Cautioned | Authority matrix should be mapped | Responded on email - Response No. 5 - On approval matrix
Legal Claim | Legal claim processing - Once payments are made and updated, the claim is marked as closed. - Verify that claims are marked as settled after payment is completed. | Cautioned | the Tab is out of the workflow. Should be included in the Work flow | Responded on email - Response No. 7
| Legal claim processing - Closed legal claims should have zero reserves. - Verify that closed legal claims have zero reserves. | Cautioned | the Tab is out of the workflow. Should be included in the Work flow | Responded on email - Response No. 7